## Tasks
Task Name | Description | Team Members | Start Date | Target End Date | Status | Task ID
API Gateway Build | Build and deploy API gateway with rate limiting and auth | Alex; Srikanth | 2026-01-15 | 2026-06-30
Dashboard UI | Frontend dashboard with charts and filters | Alex; Enith | 2026-03-01 | 2026-07-31
Auth Module | OIDC-based authentication module | Srikanth | 2026-03-15 | 2026-05-31
Perf Testing | Load and stress testing across all services | Alex; Srikanth; Enith | 2026-05-01 | 2026-08-31

## Archived Tasks
Task Name | Description | Team Members | Start Date | Target End Date | Status | Task ID
Data Migration | Migrate legacy DB to new schema | Enith | 2026-02-01 | 2026-04-30 | Closed | DRM005

## Weekly Updates
Team Member | Task | Status | Progress_Notes | Dependency | Planned_Next_Action | Hours Spent | Update Date
Alex | API Gateway Build | On Track | Route config done |  | Start auth middleware | 18 | 2026-03-23
Alex | API Gateway Build | On Track | Auth middleware started |  | Build rate limiter | 20 | 2026-03-30
Alex | API Gateway Build | On Track | Rate limiter built |  | Integration tests | 22 | 2026-04-06
Alex | API Gateway Build | On Track | Integration tests |  | Prep load testing | 20 | 2026-04-13
Alex | API Gateway Build | On Track | Load testing prep |  | Write API docs | 15 | 2026-04-20
Alex | API Gateway Build | On Track | API docs written |  | Deploy to staging | 18 | 2026-04-27
Alex | API Gateway Build | On Track | Staging deploy |  | Start load testing | 20 | 2026-05-04
Alex | API Gateway Build | On Track | Load testing started |  | Analyze results | 15 | 2026-05-11
Alex | Dashboard UI | On Track | Initial wireframes |  | Build chart components | 5 | 2026-04-13
Alex | Dashboard UI | At Risk | Chart components built |  | Build filter panel | 10 | 2026-04-20
Alex | Dashboard UI | At Risk | Filter panel done |  | Data binding | 12 | 2026-04-27
Alex | Dashboard UI | At Risk | Data binding complete |  | User testing | 12 | 2026-05-04
Alex | Dashboard UI | At Risk | Started user testing |  | Fix feedback items | 15 | 2026-05-11
Srikanth | API Gateway Build | On Track | Route config done |  | Start auth middleware | 20 | 2026-03-23
Srikanth | API Gateway Build | On Track | Auth middleware started |  | Build rate limiter | 22 | 2026-03-30
Srikanth | API Gateway Build | On Track | Rate limiter built |  | Integration tests | 18 | 2026-04-06
Srikanth | API Gateway Build | On Track | Integration tests |  | Prep load testing | 15 | 2026-04-13
Srikanth | API Gateway Build | On Track | Load testing prep |  | Write API docs | 12 | 2026-04-20
Srikanth | API Gateway Build | On Track | API docs written |  | Deploy to staging | 10 | 2026-04-27
Srikanth | API Gateway Build | On Track | Staging deploy |  | Start load testing | 8 | 2026-05-04
Srikanth | API Gateway Build | On Track | Load testing started |  | Analyze results | 5 | 2026-05-11
Srikanth | Auth Module | On Track | OIDC research |  | Provider setup | 15 | 2026-03-23
Srikanth | Auth Module | On Track | Provider setup |  | Build token flow | 18 | 2026-03-30
Srikanth | Auth Module | On Track | Token flow built |  | OIDC integration | 20 | 2026-04-06
Srikanth | Auth Module | At Risk | OIDC integration issues | Vendor delay | Follow up with vendor | 22 | 2026-04-13
Srikanth | Auth Module | At Risk | Vendor delay on certs | Vendor delay | Explore workaround | 25 | 2026-04-20
Srikanth | Auth Module | At Risk | Workaround in progress | Vendor delay | Continue workaround | 25 | 2026-04-27
Srikanth | Auth Module | At Risk | Partial integration done | Vendor delay | Integration testing | 28 | 2026-05-04
Srikanth | Auth Module | At Risk | Blocked on vendor | Vendor delay | Resolve vendor block | 30 | 2026-05-11
Enith | Data Migration | On Track | Schema mapping done |  | Write ETL scripts | 35 | 2026-03-23
Enith | Data Migration | On Track | ETL scripts written |  | Test migration | 32 | 2026-03-30
Enith | Data Migration | On Track | Test migration run |  | Data validation | 30 | 2026-04-06
Enith | Data Migration | On Track | Data validation |  | Final migration | 25 | 2026-04-13
Enith | Data Migration | On Track | Final migration |  | Cutover | 10 | 2026-04-20
Enith | Data Migration | Closed | Cutover complete |  | Post-cutover monitoring | 5 | 2026-04-27
Enith | Dashboard UI | On Track |  |  |  | 5 | 2026-03-30
Enith | Dashboard UI | On Track |  |  |  | 8 | 2026-04-06
Enith | Dashboard UI | On Track | Initial wireframes |  | Build chart components | 12 | 2026-04-13
Enith | Dashboard UI | At Risk | Chart components built |  | Build filter panel | 25 | 2026-04-20
Enith | Dashboard UI | At Risk | Filter panel done |  | Data binding | 30 | 2026-04-27
Enith | Dashboard UI | At Risk | Data binding complete |  | User testing | 32 | 2026-05-04
Enith | Dashboard UI | At Risk | Started user testing |  | Fix feedback items | 35 | 2026-05-11
Formulas:
Update Date = IF([Team Member]="","",TODAY())

## Allocations
Week Starting | Team Member | Task | Planned Hours
2026-05-18 | Alex | API Gateway Build | 15
2026-05-25 | Alex | API Gateway Build | 10
2026-06-01 | Alex | API Gateway Build | 5
2026-05-18 | Alex | Dashboard UI | 20
2026-05-25 | Alex | Dashboard UI | 20
2026-06-01 | Alex | Dashboard UI | 25
2026-06-08 | Alex | Dashboard UI | 25
2026-05-25 | Alex | Perf Testing | 5
2026-06-01 | Alex | Perf Testing | 10
2026-06-08 | Alex | Perf Testing | 15
2026-05-18 | Srikanth | API Gateway Build | 5
2026-05-25 | Srikanth | API Gateway Build | 5
2026-05-18 | Srikanth | Auth Module | 30
2026-05-25 | Srikanth | Auth Module | 25
2026-06-01 | Srikanth | Auth Module | 15
2026-06-08 | Srikanth | Auth Module | 10
2026-05-25 | Srikanth | Perf Testing | 10
2026-06-01 | Srikanth | Perf Testing | 20
2026-06-08 | Srikanth | Perf Testing | 25
2026-05-18 | Enith | Dashboard UI | 30
2026-05-25 | Enith | Dashboard UI | 25
2026-06-01 | Enith | Dashboard UI | 15
2026-06-08 | Enith | Dashboard UI | 10
2026-05-18 | Enith | Perf Testing | 5
2026-05-25 | Enith | Perf Testing | 10
2026-06-01 | Enith | Perf Testing | 20
2026-06-08 | Enith | Perf Testing | 25

## Lookups
Team Members | Members | Task Statuses | Update Statuses
Alex | Alex | Not Started | On Track
Srikanth | Srikanth | In Progress | At Risk
Enith | Enith | On Track | Blocked
Alex; Srikanth |  | At Risk | Closed
Alex; Enith |  | Blocked
Srikanth; Enith |  | Closed
Alex; Srikanth; Enith